## Sheet1
Task Name | Assignee | Expected Time | Actual Time | Task Status
port driver | Amr/ Aatef | 2 days | 2 days | done
DIO driver | Aatef | 1 day | 1 day | done
LED driver | Amr | 1 hour | 1 hour | done
Button driver | Aatef | 1 hour | 1 hour | done
Hardware Test | Aatef | repetitive | - | done
Design document | Amr | 5 hours | 5 hours | done